## ProLog
Final Project | PC Hardware Bot ¦ YouTube Q&A ¦ Progress Tracking Sheet
Status | Area | Task | Priority | EstimateHours | Notes
Complete | Planning | Freeze MVP scope + success criteria | P0 | 0.5 | Stack builder + timestamp evidence + gated web lane
Backlog | Planning | Create videos.csv manifest (30 videos) | P0 | 2 | Include tags: case/cpu/gpu/psu/sff/mini/ai
Backlog | Data | Verify transcript availability for each video | P0 | 1 | Prefer videos where YouTube shows transcript (captions exist)
Backlog | Data | Manual transcript/subtitle capture for first 15 videos | P0 | 3 | Use Show transcript when captions exist
Backlog | Scripts | Write normalise_subtitles script -> segments.jsonl | P0 | 3 | Parse VTT/SRT; store t_start/t_end; build url_at_t_start
Backlog | Indexing | Build Chroma index + persist_directory | P0 | 2 | Local-first iteration
Backlog | Retrieval | Chunking config: turn-aware grouping + Recursive splitter | P0 | 2.5 | Tune for benchmark queries
Backlog | Data | Manual transcript/subtitle capture for remaining 15 videos | P0 | 3 | Target 30 total by end of Day 2
Backlog | QC | QC pass: numbers/units, dedupe, empty segments | P1 | 2 | Spot-check GPU/CPU model strings and FPS/W/°C
Backlog | RAG | Implement retrieve tool (top-k + metadata filters) | P0 | 2 | Filter by component tag and channel
Backlog | RAG | Answer generator with structured JSON output | P0 | 3 | answer + sources[] + stack_update + warnings[]
Backlog | Stack | Define stack schema + persistence (db/json store) | P0 | 3 | Items: part type, model, constraints, evidence
Backlog | Stack | Constraint engine (case->mobo, psu->gpu) | P0 | 3 | Keep rules lightweight; surface risks not guarantees
Backlog | Agent | Agent router: stack mode vs QA mode vs web lane | P0 | 2 | Gate web lane behind intent + warnings
Backlog | Credibility | Implement sponsorship/credibility card (Level A) | P1 | 3 | Use YouTube paid promotion cues language; cite evidence
Backlog | Web | Implement web lane: news + retailer search prompt | P1 | 3 | Return citations; avoid giving definitive prices
Backlog | UI | Lovable UI: chat + evidence cards + stack panel | P0 | 6 | Buttons: Like/Replace/More options/Save stack
Backlog | UI | Save/retrieve stack endpoint + UI binding | P0 | 2 | Persist by session_id; export as JSON + prompt card
Backlog | Observability | Enable LangSmith tracing from Day 2+ | P0 | 1 | Project naming; capture tool calls
Backlog | Evaluation | Create 30–60 QA pairs dataset | P0 | 4 | Include expected evidence (video_id + timestamp ranges)
Backlog | Evaluation | Run LangSmith eval experiment + analyse failures | P0 | 3 | Track retrieval hit rate + answer faithfulness
Backlog | Safety | Add AI disclosure + EU transparency copy | P0 | 1 | Inform users they interact with AI
Backlog | Safety | GDPR-style data minimisation + retention note | P1 | 1 | Store minimal stack data; limit logging
Backlog | Safety | Overclocking/XMP safety warnings + refusal gates | P0 | 2 | Intel warns altering frequency/voltage may void warranty
Backlog | Deploy | Deploy backend + env vars + health checks | P0 | 3 | Stable public URL for demo
Backlog | Docs | Write README + architecture diagrams + limitations | P0 | 3 | Include evaluation results + traces screenshots
Backlog | Slides | Create demo script + slides | P0 | 3 | Problem -> solution -> architecture -> eval -> demo
Backlog | Rehearsal | Full rehearsal + backup demo prompts | P0 | 3 | Prepare offline screenshots if needed
Note: | Please see tabs below to navigate.
Day | Output you must have by end of day | Allocation (approx.)
Day 1 | Repo scaffold + 10–15 videos fully normalised into JSONL + working Chroma index | 2h repo & env, 3–4h transcript capture/normalise, 2h chunk+embed baseline
Day 2 | All 30 videos normalised, stable chunking, retrieval returns good benchmark moments | 3h capture/normalise remainder, 2h QC, 3h retrieval tuning
Day 3 | Agent with tools + stack state persisted + structured output schema | 3h agent/tools, 2h stack persistence, 3h evidence cards + constraints
Day 4 | Web app integrated (Lovable) + credibility/sponsorship card + gated “news/shopping” lane | 4h UI integration, 2h credibility tool, 2h web lane gate + citations
Day 5 | Deployed demo + LangSmith traces + evaluation run + bug fixes | 2h deploy, 3h evaluation dataset + run, 3h fixes + polish
Day 6 | Documentation + slides + rehearsal + “demo resilience” (backup prompts) | 2h docs, 2h slides, 3h rehearsal, 1h packaging
Day | Output you must have by end of day | Allocation (approx.)
Day 7 | Repo scaffold + 10–15 videos fully normalised into JSONL + working Chroma index | 2h repo & env, 3–4h transcript capture/normalise, 2h chunk+embed baseline
Day 8 | All 30 videos normalised, stable chunking, retrieval returns good benchmark moments | 3h capture/normalise remainder, 2h QC, 3h retrieval tuning
Day 9 | Agent with tools + stack state persisted + structured output schema | 3h agent/tools, 2h stack persistence, 3h evidence cards + constraints
Day | Output you must have by end of day | Allocation (approx.)
Day 7 | Repo scaffold + 10–15 videos fully normalised into JSONL + working Chroma index | 2h repo & env, 3–4h transcript capture/normalise, 2h chunk+embed baseline
Day 8 | All 30 videos normalised, stable chunking, retrieval returns good benchmark moments | 3h capture/normalise remainder, 2h QC, 3h retrieval tuning
Day 9 | Agent with tools + stack state persisted + structured output schema | 3h agent/tools, 2h stack persistence, 3h evidence cards + constraints
Day 10 | Web app integrated (Lovable) + credibility/sponsorship card + gated “news/shopping” lane | 4h UI integration, 2h credibility tool, 2h web lane gate + citations
Day 11 | Deployed demo + LangSmith traces + evaluation run + bug fixes | 2h deploy, 3h evaluation dataset + run, 3h fixes + polish
Day 12 | Documentation + slides + rehearsal + “demo resilience” (backup prompts) | 2h docs, 2h slides, 3h rehearsal, 1h packaging
Day | Output you must have by end of day | Allocation (approx.)

## YT - ScrapeList
Done | Priority | Channel | Video (title) | video_id | Stack coverage & why it’s good for RAG | Notes:
FALSE | 1 | Gamers Nexus | “$13K of GPU Test Methodology: Airflow Photography, RTX …” | -P7-ML-bPCE | Benchmark methodology vocabulary improves retrieval for “benchmark moment finder”.
FALSE | 2 | Gamers Nexus | “The Problem with GPU Benchmarks ¦ Reality vs. Numbers …” | qDnXe6N8h_c | Great for credibility card signals: methodology caveats, sources of error.
FALSE | 3 | Gamers Nexus | “Intel’s Major Overhaul for CPU & GPU Benchmarking ¦ ‘GPU Busy’” | 5hAy5V91Hr4 | Adds benchmark interpretation concepts useful in Q&A UX.
FALSE | 4 | Gamers Nexus | “Best PC Cases of 2025: $75 to $200 Airflow, Thermals …” | 2gCFdN7J4sk | Case slot: shortlist of cases + why (thermals, airflow, build quality).
FALSE | 5 | Gamers Nexus | “Best PC Cases of 2024: $80 to $800 Airflow …” | 2RytD3xII-0 | Case slot: broader tiering; helps budget vs premium queries.
FALSE | 6 | Gamers Nexus | “Best PC Cases for 2025 So Far ¦ Computex Round‑Up …” | gnv2spLqGss | Future‑proofing: recent releases; good for “show me 5 more” options.
FALSE | 7 | Gamers Nexus | “Fractal North XL Case Review & Benchmarks …” | aQHKCjuYTVQ | Deep single‑case review yields rich timestampable evidence.
FALSE | 8 | Gamers Nexus | “Best Case of 2024 So Far: Antec Flux Pro Review & Benchmarks” | IqLyqUdQNcg | Case slot: clear thermal/noise/build discussion for evidence cards.
FALSE | 9 | Gamers Nexus | “Surprisingly Good: Antec C8 ARGB Case Review, Thermals …” | yJAq2H52A2A | Case slot: “value vs premium” narrative; lots of comparative language.
FALSE | 10 | Optimum Tech | “Cooler Master NR200P PC Build Guide (AIO & Horizontal GPU)” | JXl20U1f4co | SFF flow + compatibility constraints; useful for form‑factor reasoning.
FALSE | 11 | Optimum Tech | “Cooler Master NR200P MAX PC Build Guide + Thermals …” | 3Wo-ceEIh6A | SFF thermal constraints and build steps → great “stacking” UX.
FALSE | 12 | Optimum Tech | “K39 Review – Ultimate Sub 5L Case?” | dyCtUyDmAdU | Extreme SFF constraints; drives your “case → parts constraints” logic.
FALSE | 13 | Optimum Tech | “The Smallest ITX Gaming Case Ever (3.1L)” | GqJFyaAT81E | Adds “fun mode” (extreme builds) while still technical.
FALSE | 14 | Optimum Tech | “RTX 3080 FE vs ITX – Round 2!” | EUSDCyqv8OQ | GPU cooling orientation + case interaction; great for constraints engine.
FALSE | 15 | Hardware Unboxed | “Ryzen 5 7500F vs. Core i5‑12400F, Gaming Benchmarks” | gJc0fIyy6s4 | CPU slot: “budget CPU decision” with benchmark‑dense talk.
FALSE | 16 | Hardware Unboxed | “AMD Ryzen 7 7800X3D Revisit: It Remains The Best Gaming …” | 91_VxiQMJtw | CPU slot: evergreen “best gaming CPU” narrative; good retrieval anchor.
FALSE | 17 | Hardware Unboxed | “Ryzen 7 7800X3D vs 9800X3D, Which Should You Buy?” | X0oimg79NZ8 | CPU compare template; good for “compare across videos” value.
FALSE | 18 | Hardware Unboxed | “Intel Core Ultra 7 265K Review, vs. 7800X3D …” | 9RcYrliKgvg | CPU compare across vendors; improves “intel/amd/both” flow.
FALSE | 19 | Hardware Unboxed | “Top Tier AM5 Gaming for Less, 7500X3D vs. 9800X3D …” | fhLuHO1qjLU | CPU value analysis; helps budget‑tier stack building.
FALSE | 20 | Hardware Unboxed | “Bring This Back! Ryzen 7 5800X3D & 5700X3D Revisit 2026” | c7Au9Lb5Kw4 | Upgrade path discussion; great for “reuse old parts” Q&A.
FALSE | 21 | Hardware Unboxed | “Best Budget GPU: RTX 5060 vs RX 9060 XT vs Arc B580” | xlbNsP5ySmA | GPU slot: modern budget fight; benchmark comparisons.
FALSE | 22 | Hardware Unboxed | “Best Value Graphics Cards of 2025 (10 Country Analysis)” | mPQWoSEYMLs | Great for EU vs other region pricing narrative (even if prices change).
FALSE | 23 | Hardware Unboxed | “FSR 3.1 vs DLSS 3.7 vs XeSS 1.3 Upscaling Battle …” | YZr6rt9yjio | “feature‑aware GPU choosing” (upscalers), common buyer question.
FALSE | 24 | Hardware Unboxed | “Arc B580 vs RTX 5050 – XeSS vs DLSS 4 Performance …” | lLe5AP6igjw | Adds Intel GPU lane; supports “budget inference GPU” discussions.
FALSE | 25 | Gamers Nexus | “NVIDIA GeForce RTX 5090 Founders Edition Review …” | VWSlOC_jiLQ | High‑end GPU lane; supports “fun/max budget” mode.
FALSE | 26 | Gamers Nexus | “Dual‑GPU Fake Frame Latency Benchmarks: $7 Lossless …” | GDvfIbRIb3U | Latency/frametime concepts; great credibility and methodology content.
FALSE | 27 | Gamers Nexus | “Wasting Money on Power Supplies: How Many Watts You Need …” | X_wtoCBahhM | PSU sizing is critical for compatibility; transcript likely includes wattage reasoning.
FALSE | 28 | ServeTheHome | “The PERFECT $200 10GbE Mini PC?” | Z-3ZjMSEEc8 | Office/mini‑PC lane; also helps “quiet small PC” users.
FALSE | 29 | ServeTheHome | “The Pinnacle of Mini PC Servers – Minisforum MS‑01” | d3j4aEAZR7w | Mini workstation/IO angle; good for productivity and small builds.
FALSE | 30 | Level1Techs | “TINY 70 watt RTX 4000 SFF ADA … for AI …” | ZiPmT_JWNII | AI/workstation lane + small form factor GPU constraints.